## Sheet1
Phase | Document name | Version | Author | Reviewer | Starting Date | Date of completion | In Final Folder?
| Feasibility Report | 1 | Pinky J. Meena | Sushant Pritmani |  | 16th Jan 2013 | DONE
| Project Proposal | 1 | Vidhan,Jayesh,Ishita | Vipul, Ayush |  | 16th Jan 2013 | Done
| Project Plan | 1 | Nalin, Anubhav | Dishant |  | 27th Jan 2013 | Done
| SDLC | 1 | Vipul | Jayesh |  | 6th Feb 2013 | Done
| Project Plan | 2 | Vipul | Ayush | 12th Feb 2013 | 13th Feb 2013 | Done
| Requirement Analysis Report | 1 | Ayush, Vidhan | Sushant, Anubhav |  | 13th Feb 2013
Requirement(1) | SRS Increment-1 | 1 | Ayush, Ishita, Vidhan | Vipul, Pinky | 13th Feb 2013 | 17th Feb 2013 | Done
| Draft User Manual | 1 | Pinky, Sushant | Nalin | 13th Feb 2013 | 18th Feb 2013 | Done
| Traceability matrix | 1 | Dishant, Anubhav | Vidhan | 13th Feb 2013 | 19th Feb 2013
| Test Plan | 1 | Vipul, Jayesh, Nalin | Ishita, Anubhav | 13th Feb 2013 | 19th Feb 2013 | Done
* = proposed submission date
Requirement(2) | SRS Increment-2 | 2 | Anubhav, Sushant | Pinky |  | 1st March 2013 | Done
| Draft User Manual | 2 | Pinky J. Meena | Anubhav |  | 4th March 2013 | Done
| Test Plan | 2 | Sushant NAlin | Jayesh |  | 7th March 2013 | Done
| Traceability Matrix | 2 | Sushant | Dishant |  | 8th March 2013
Design(1) | Database Modeling | 1 | Ayush, Jayesh | Vipul
| Use case Diagrams | 1 | Anubhav,Ishita | Pinky
| Class Diagram | 1 | Vidhan,Vipul | Nalin
| Sequence Diagram | 1 | Dishant | Ayush
| Activity Diagram | 1 | Anubhav,Pinky | Ishita
| SDD Increment-1 | 1 | Nalin, Sushant | Ishita Vidhan |  | 25th Feb | Done
| Test Cases Increment1 | 1 | Anubhav | Nalin |  | 1st March | Done
Design(2) | SDD Increment-2 | 2 | Sushant Nalin | Vipul Pinky |  | 5th March 2013 | Done
| Test Cases Increment-2 | 1 | Anubhav | Nalin |  | 22nd March | not in final submission as only latest version is included
| Test Cases Increment-2 | 1.1 | Anubhav | Nalin |  | 24th March | Done
Coding Standards
| Risk Management | 1 | Pinky, Ishita | Nalin |  | 7th April 2013 | Done
| Quality Assuarance | 1 | Ishita, Pinky | Anubhav |  | 1st April 2013 | Done
Testing1 | Test Report(1) | 1 | Vidhan Nalin | Sushant |  | 18th March 2013 | Done
Testing2 | Test Report(2) | 2 | Vidhan Nalin | Sushant |  | 7th April 2013 | Done
| Termination Analysis | 1 | Jayesh | Nalin |  | 9th April 2013
| Installation Manual | 1 | Dishant | Vidhan |  | 9th April 2013 | Done
| Gannt Chart |  | Nalin | Dishant |  | 10th April | Done
| User Manual |  | Pinky | Ishita |  | 9th April 2013 | Done